## Sheet1
Project Name Backlog
Members: | Henry Pham, Shashank Sridhar, Daniel Bao, Yipeng Liu
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
Team Reg | Form submission | 4 | Yipeng Liu | Completed | 2021-10-15 | 2021-10-15 | Submitted.
| Class compare wild fires vs droughts | 1 | Daniel Bao | In Progress | 2021-10-15 |  | Java
| Create icons/county images for the website | 1 | Daniel Bao | In Progress | 2021-10-15
Website | Home Page (HTML + CSS) | 1 | Yipeng Liu | Completed | 2021-10-15 | 2021-10-16 | Used a template
Map | Interactive Map | 2 | Yipeng Liu | In Progress | 2021-10-16 |  | not working

## Utils (hidden)
Priority | Status | Member | All | Henry Pham | Shashank Sridhar | Daniel Bao | Yipeng Liu
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed